## Product Backlog
Epic ID | Epic | Story ID | User Story | Requirement ID(s) | Acceptance Criteria | Priority | Story Points | Sprint
EPIC-01 | AI Customer Chatbot | US-01-01 | As a customer, I want to interact with an AI-powered chatbot so that I can obtain banking and KYC assistance through a conversational interface. | FR-001 | Given the chatbot service is available, when a customer starts a conversation, then the system shall accept the interaction and provide a response. | Must Have | 5 | Sprint 1
EPIC-01 | AI Customer Chatbot | US-01-02 | As a customer, I want to ask questions in natural language so that I do not need to use predefined commands. | FR-002, AI-001 | Given a natural-language query, when it is submitted, then the chatbot shall interpret the query and return a relevant response. | Must Have | 5 | Sprint 1
EPIC-01 | AI Customer Chatbot | US-01-03 | As a customer, I want the chatbot to identify my request intent so that my query is handled by the appropriate capability. | AI-002 | Given a supported customer query, when the chatbot processes it, then the correct intent shall be identified. | Must Have | 5 | Sprint 1
EPIC-01 | AI Customer Chatbot | US-01-04 | As a customer, I want the chatbot to extract useful information from my message so that my request can be processed efficiently. | AI-003 | Given a message containing relevant entities, when it is processed, then the applicable information shall be extracted. | Should Have | 5 | Sprint 1
EPIC-01 | AI Customer Chatbot | US-01-05 | As a customer, I want relevant and contextual answers to KYC and banking questions so that I can complete tasks with minimal assistance. | FR-003, AI-004 | Given a supported KYC or banking query, when processed, then the chatbot shall return a contextually relevant answer. | Must Have | 8 | Sprint 1
EPIC-01 | AI Customer Chatbot | US-01-06 | As a customer, I want differently worded versions of the same request to be understood consistently. | AI-005 | Given equivalent queries with different wording, when submitted, then the chatbot shall identify the same intended request. | Should Have | 5 | Sprint 1
EPIC-01 | AI Customer Chatbot | US-01-07 | As a customer, I want a clear fallback response when the chatbot cannot understand my request. | AI-006 | Given an unsupported or unclear query, when processing fails, then the chatbot shall provide an appropriate fallback response. | Must Have | 3 | Sprint 1
EPIC-01 | AI Customer Chatbot | US-01-08 | As a platform owner, I want irrelevant or inappropriate chatbot responses to be identified and prevented. | AI-007 | Given an unsupported or inappropriate request, when processed, then the chatbot shall not provide an unsafe or irrelevant supported-service response. | Must Have | 8 | Sprint 1
EPIC-01 | AI Customer Chatbot | US-01-09 | As a Test Manager, I want AI-generated responses to be evaluated so that chatbot quality can be assessed systematically. | AI-008, NFR-009 | Given a defined set of test prompts, when chatbot responses are evaluated, then results shall be recorded for consistency and relevance. | Must Have | 5 | Sprint 4
EPIC-02 | KYC Management | US-02-01 | As a customer, I want to submit my identity and KYC information so that my profile can be verified. | FR-004 | Given the KYC form is available, when mandatory customer information is entered, then the system shall accept it for validation. | Must Have | 5 | Sprint 2
EPIC-02 | KYC Management | US-02-02 | As a customer, I want mandatory KYC fields to be validated before submission so that incomplete applications are prevented. | FR-005 | Given a KYC submission, when a mandatory field is missing or invalid, then submission shall be prevented and an actionable validation message shown. | Must Have | 5 | Sprint 2
EPIC-02 | KYC Management | US-02-03 | As a compliance user, I want incomplete or invalid KYC information to be identified so that records can be corrected or rejected. | FR-006 | Given invalid or incomplete KYC data, when validation runs, then the affected fields and validation outcome shall be identified. | Must Have | 5 | Sprint 2
EPIC-02 | KYC Management | US-02-04 | As an authorized user, I want verified KYC records maintained so that customer information is available for processing and verification. | FR-007 | Given a valid KYC record, when it is accepted, then the record shall be stored and retrievable by authorized users. | Must Have | 8 | Sprint 2
EPIC-02 | KYC Management | US-02-05 | As a Test Manager, I want realistic synthetic KYC customers so that KYC tests can be executed without using real customer data. | FR-008, NFR-007 | Given the KYC data generator, when executed, then it shall create realistic synthetic records covering required test fields. | Should Have | 5 | Sprint 2
EPIC-03 | AML Monitoring | US-03-01 | As a compliance officer, I want transactions evaluated against predefined AML risk scenarios so that potentially suspicious activity can be detected. | FR-009 | Given a transaction and configured AML scenarios, when analysis runs, then matching risk scenarios shall be identified. | Must Have | 8 | Sprint 3
EPIC-03 | AML Monitoring | US-03-02 | As a Test Manager, I want synthetic AML transaction data so that normal and suspicious transaction patterns can be tested safely. | FR-010 | Given the AML data generator, when executed, then it shall create transactions suitable for defined AML test scenarios. | Must Have | 5 | Sprint 3
EPIC-03 | AML Monitoring | US-03-03 | As a compliance officer, I want suspicious transaction patterns identified so that potentially risky activity can be investigated. | FR-011 | Given a transaction history, when configured pattern checks run, then suspicious patterns shall be identified. | Must Have | 8 | Sprint 3
EPIC-03 | AML Monitoring | US-03-04 | As a compliance officer, I want suspicious transactions to generate alerts so that they can be reviewed promptly. | FR-012 | Given a transaction meeting an alert condition, when AML processing completes, then an alert shall be generated with the relevant transaction reference. | Must Have | 5 | Sprint 3
EPIC-03 | AML Monitoring | US-03-05 | As an authorized compliance user, I want to review AML alerts so that suspicious activity can be assessed. | FR-013, NFR-002 | Given an authorized user and an AML alert, when the alert is opened, then the user shall be able to review its relevant details. | Must Have | 5 | Sprint 3
EPIC-03 | AML Monitoring | US-03-06 | As a Test Manager, I want AML scenarios to include both normal and suspicious activity so that the test suite covers different risk outcomes. | FR-009, FR-011, FR-012 | Given the AML scenario dataset, when tests run, then both expected non-alert and alert outcomes shall be represented. | Should Have | 5 | Sprint 3
EPIC-04 | Banking System Integration | US-04-01 | As a platform owner, I want the platform integrated with existing customer and banking systems so that required information can be exchanged. | FR-014 | Given configured integration endpoints, when a supported request is made, then the platform shall communicate with the required existing system. | Must Have | 8 | Sprint 2
EPIC-04 | Banking System Integration | US-04-02 | As a platform owner, I want customer and transaction information exchanged correctly between systems so that downstream processing receives complete data. | FR-015 | Given valid source data, when an integration transaction occurs, then required fields shall be transferred without unintended alteration. | Must Have | 8 | Sprint 3
EPIC-04 | Banking System Integration | US-04-03 | As a platform owner, I want temporary integration failures handled safely so that customer and transaction data is not corrupted. | FR-016, NFR-008 | Given a temporary integration failure, when the operation fails, then the system shall handle the failure gracefully and preserve data integrity. | Must Have | 8 | Sprint 3
EPIC-05 | Security & Audit | US-05-01 | As a platform owner, I want sensitive KYC information protected so that unauthorized parties cannot access it. | NFR-001 | Given protected customer information, when an unauthorized access attempt occurs, then access shall be denied. | Must Have | 8 | Sprint 4
EPIC-05 | Security & Audit | US-05-02 | As a system administrator, I want role-based access so that users can access only the capabilities appropriate to their roles. | NFR-002 | Given a user role, when the user accesses a protected capability, then access shall be granted or denied according to the configured role. | Must Have | 5 | Sprint 4
EPIC-05 | Security & Audit | US-05-03 | As a platform owner, I want customer information protected for confidentiality and integrity throughout processing. | NFR-003 | Given customer information, when it is stored or processed, then unauthorized modification or disclosure shall be prevented. | Must Have | 8 | Sprint 4
EPIC-05 | Security & Audit | US-05-04 | As a compliance user, I want important KYC and AML activities recorded so that actions can be audited. | NFR-004 | Given a significant KYC or AML action, when it occurs, then an auditable record shall be created with relevant event information. | Must Have | 5 | Sprint 4
EPIC-06 | Scalability & Performance | US-06-01 | As a platform owner, I want the chatbot to support multiple concurrent interactions so that customers can use the service at the same time. | FR-017 | Given multiple concurrent users within the expected workload, when requests are submitted, then the platform shall process them without unacceptable degradation. | Should Have | 8 | Sprint 4
EPIC-06 | Scalability & Performance | US-06-02 | As a platform owner, I want the platform to support increasing customer and transaction volumes so that it can grow with demand. | FR-018, NFR-006 | Given increasing workload levels, when volume grows, then the platform shall maintain stable operation within the planned capacity. | Should Have | 8 | Sprint 4
EPIC-06 | Scalability & Performance | US-06-03 | As a customer, I want chatbot responses within an acceptable time so that interactions feel responsive. | FR-019, NFR-005 | Given normal operating conditions, when a supported query is submitted, then the response shall be delivered within the defined performance target. | Must Have | 5 | Sprint 4
EPIC-06 | Scalability & Performance | US-06-04 | As a Test Manager, I want performance tests to use representative synthetic data so that test results reflect realistic workloads without exposing real customer data. | FR-020, NFR-007 | Given representative synthetic datasets, when performance tests execute, then workload and response metrics shall be captured. | Should Have | 8 | Sprint 4
EPIC-07 | Reliability & Maintainability | US-07-01 | As a customer, I want repeated valid requests to produce consistent outcomes so that the service is predictable. | NFR-009 | Given identical valid inputs and equivalent conditions, when the request is repeated, then the expected result shall remain consistent. | Must Have | 5 | Sprint 4
EPIC-07 | Reliability & Maintainability | US-07-02 | As a platform owner, I want KYC and AML rules to be maintainable so that rule updates do not require major system changes. | NFR-010 | Given an authorized rule update, when a KYC or AML rule changes, then the affected rule shall be updateable without major system redesign. | Should Have | 8 | Sprint 4
EPIC-08 | Quality Engineering & Test Automation | US-08-01 | As a Test Manager, I want testable requirements and traceability so that every important requirement can be validated through the testing lifecycle. | FR-001, FR-004, FR-009, FR-014, FR-019, NFR-001, NFR-004 | Given a baselined requirement, when the backlog and test suite are prepared, then the requirement shall be traceable to relevant tests and results. | Must Have | 5 | Sprint 1
EPIC-08 | Quality Engineering & Test Automation | US-08-02 | As a Test Manager, I want automated Jest tests for unit and integration scenarios so that test execution is repeatable and measurable. | FR-008, FR-010, FR-020 | Given the prepared synthetic datasets and test scenarios, when Jest is executed, then automated test results shall be produced. | Must Have | 8 | Sprint 4

## Epic Summary
Epic ID | Epic | Stories | Total Story Points | Primary Sprint
EPIC-01 | AI Customer Chatbot | 9 | 49 | Sprint 1
EPIC-02 | KYC Management | 5 | 28 | Sprint 2
EPIC-03 | AML Monitoring | 6 | 36 | Sprint 3
EPIC-04 | Banking System Integration | 3 | 24 | Sprint 2
EPIC-05 | Security & Audit | 4 | 26 | Sprint 4
EPIC-06 | Scalability & Performance | 4 | 29 | Sprint 4
EPIC-07 | Reliability & Maintainability | 2 | 13 | Sprint 4
EPIC-08 | Quality Engineering & Test Automation | 2 | 13 | Sprint 1

## Sprint Summary
Sprint | Focus | Stories | Story Points
Sprint 1 | Requirements traceability, AI chatbot and NLP foundation | 9 | 49
Sprint 2 | KYC management, synthetic KYC data and core integration | 6 | 36
Sprint 3 | AML monitoring, synthetic AML data and integration resilience | 8 | 52
Sprint 4 | Security, audit, scalability, performance and automation | 12 | 81

## Requirement Coverage
Requirement ID | Requirement | Mapped User Stories
FR-001 | AI-powered chatbot for customer interaction | US-01-01, US-08-01
FR-002 | Chatbot understands natural-language customer queries | US-01-02
FR-003 | Relevant responses for KYC and banking-service queries | US-01-05
FR-004 | Customer identity/KYC information collection | US-02-01, US-08-01
FR-005 | Validation of mandatory KYC information | US-02-02
FR-006 | Identification of incomplete or invalid KYC information | US-02-03
FR-007 | Maintenance of customer KYC records | US-02-04
FR-008 | Generation and processing of synthetic customer data for KYC testing | US-02-05, US-08-02
FR-009 | Identification of transactions matching predefined AML risk scenarios | US-03-01, US-03-06, US-08-01
FR-010 | Generation of synthetic AML transaction data | US-03-02, US-08-02
FR-011 | Identification of suspicious transaction patterns | US-03-03, US-03-06
FR-012 | Generation of alerts for potentially suspicious transactions | US-03-04, US-03-06
FR-013 | Authorized review of AML alerts | US-03-05
FR-014 | Integration with existing banking/customer systems | US-04-01, US-08-01
FR-015 | Exchange of customer and transaction information with integrated systems | US-04-02
FR-016 | Safe handling of integration failures | US-04-03
FR-017 | Support for multiple concurrent customer interactions | US-06-01
FR-018 | Support for increasing customer and transaction volumes | US-06-02
FR-019 | Acceptable response times under expected workloads | US-06-03, US-08-01
FR-020 | Performance testing using representative synthetic data | US-06-04, US-08-02
NFR-001 | Protection of sensitive customer and KYC information | US-05-01, US-08-01
NFR-002 | Role-based access for authorized users | US-03-05, US-05-02
NFR-003 | Confidentiality and integrity of customer information | US-05-03
NFR-004 | Audit information for important KYC and AML activities | US-05-04, US-08-01
NFR-005 | Acceptable chatbot response time under normal conditions | US-06-03
NFR-006 | Stable performance as user numbers increase | US-06-02
NFR-007 | Processing of large volumes of synthetic test data | US-02-05, US-06-04
NFR-008 | Graceful recovery from temporary integration/service failures | US-04-03
NFR-009 | Consistent results for identical valid inputs | US-01-09, US-07-01
NFR-010 | Maintainable KYC/AML rules without major system changes | US-07-02
AI-001 | Interpret natural-language customer queries | US-01-02
AI-002 | Identify customer-query intent | US-01-03
AI-003 | Extract relevant information from customer messages | US-01-04
AI-004 | Provide contextually relevant responses | US-01-05
AI-005 | Handle wording variations for similar requests | US-01-06
AI-006 | Respond appropriately when a query cannot be processed | US-01-07
AI-007 | Prevent inappropriate or irrelevant responses | US-01-08
AI-008 | Evaluate AI-generated responses as part of testing | US-01-09

## Planning Notes
Item | Decision / Rationale
Estimation scale | Fibonacci-style story points: 1, 2, 3, 5, 8. Larger items should be decomposed during refinement.
Prioritization | Must Have items support core platform operation, compliance workflows, security, or required testing. Should Have items improve coverage, scalability, maintainability, or supporting capabilities.
Sprint allocation | Four illustrative two-week sprints are used to organize the project deliverables. Exact dates can be added when the project schedule is finalized.
Acceptance criteria | Criteria are written so that each story can later be converted into test scenarios and automated Jest tests.
Traceability | Requirement IDs are retained from the Requirements Specification so that the backlog can feed the RTM without changing identifiers.
GenAI role | Generative AI is used to accelerate story drafting, acceptance-criteria generation, decomposition ideas, and prioritization suggestions. Final backlog decisions remain subject to Test Manager review.